## Project schedule
| Chapter 4 and 5 assignment |  |  |  | Project start: | [7 empty] | 2025-10-17
| Name: Yousuf, Justin, Cyantan, Fahim, Esfar |  |  |  | Display week range: | [7 empty] | 1
Filled out by: Fahim Tanvir(Group leader)
[5 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01
| TASK | START | END | time axis 2025-10-13 to 2025-12-07
 | time axis 2025-10-13 to 2025-12-07
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Setting up Github repo | 2025-10-17 | 2025-10-20 | 4
| Do SQL Noir | 2025-10-17 | 2025-10-21 | 5
| Formulate 7 mysteries(21-28 propositions) each member | 2025-10-21 | 2025-10-24 | 4
| Partners/people will record walkthrough of mysteries | 2025-10-23 | 2025-10-25
| Everything uploaded to googledrive and github to be analyzed and critiqued by project leader | 2025-10-23 | 2025-10-26 | 4
| Explanations/Assitance | 2025-10-23 | 2025-10-23 | 1
| Each pairwill explain what they did and learned based on NACE competencies, through video/ppt | 2025-10-23 | 2025-10-26 | 4
| Create Presentation (Mp4) | 2025-10-23 | 2025-10-26
| Project leader checks everyones work | 2025-10-23 | 2025-10-26 | 4
| Finalize Submission | 2025-10-23 | 2025-10-26 | 4