## Group member 4
To-do list |  |  |  | Group: 10:45 Am Section, Members: Fahim, Yousuf(Pair 1), Justin, Sayantan(Pair 2), Esfar(Individual)
To be completed by: |  | 2025-10-26 |  | Name: Fahim Tanvir(Project Leader)
Deadline: |  | 2025-10-26 |  | Date: 01/17/2025
PROJECT LEADER WILL WRITE ANY ADDITIONAL NOTES THEY TOOK IN RED
Project 1.
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-10-17 | 2025-10-18 | 2025-10-20 | 3 | Communicate as a group to review the professor’s assignment instructions and feedback/criticisms from last assignments. Assign roles (e.g. drafting individual's propositions, setting deadlines, undertanding topics, who writes explanations, who manages GitHub). Fahim is assigned as group leader(he is filling this document out and the GANT chart). Agree on internal deadlines before the official due date.
100% | Research & Preparation | 2025-10-17 | 2025-10-19 | 2025-10-21 | 4 | All members will play SQL Noir and get past beginner stage. YOUSUF, FAHIM AND ESFAR finished by the original due date, SAYANTAN AND JUSITN FINISHED BY THE REVISED.
100% | Drafting Propositions and Writing Queries | 2025-10-21 | 2025-10-23 | 2025-10-24 | 3 | Brainstorm 7 different mysteries (2 per group member) and a mystery to pair with it. Each pair will look through and mess around with each database(Esfar and Pair 2(Justin and Sayantan) will choose WorldwideImporters, Pair 1(Fahim and Yousuf) will choose AdventureWorks)
100% | Team solving | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2 | For the pairs, each member will solve eachothers mysteries within a live call. Make it 3-4 queries max.
100% | Create Videos | 2025-10-23 | 2025-10-24 | 2025-10-26 | 3 | When each pair is done, they will save a recording of their session and upload it on youtube. NOT BEFORE A FINAL CHECK WITH FAHIM! SO send it to the google drive for him to look.
100% | Final Submission | 2025-10-23 | 2025-10-24 | 2025-10-26 | 3 | Group will submit any recent and updated files on the github. Fahim(person filling this out) will submit github link. Final submission made in 10:00 pm.